## Project Planner
Project CERA-WOLRD OF TILES _Planner
|  |  |  | Select a period to highlight at right. A legend describing the charting follows. |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY/TASK: | Task Owner: | Task Supporters: | Remarks | PLAN START (Date) | PLAN DURATION | ACTUAL START (Date) | ACTUAL DURATION | PERCENT COMPLETE | Novemeber - Day
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Reply to Aptech India | Huy, Duc, Duong, Trung |  | Done: Huy | 1 | 1 | 1 | 1 | 100%
Project Analysis, Scope, Framework | Huy |  |  | 1 | 1 | 1 | 1 | 100%
Tasks Assignment Discussion | Huy, Duc, Duong, Trung |  | Request to meet online | 1 | 1 | 1 | 1 | 100%
Domain, Frame for Web | Duc | Duong, Huy, Trung |  | 1 | 5 | 1 | 5 | 100%
Brainstorming | Huy, Duc, Duong, Trung |  |  | 1 | 2 | 1 | 1 | 100%
Picture Collection | Huy, Duc, Duong, Trung |  |  | 4 | 5 | 4 | 5 | 100%
Wall Tile Pictures + Feature | Duong |  |  | 4 | 5 | 4 | 5 | 100%
Floor Tile + features | Trung |  |  | 4 | 5 | 4 | 5 | 100%
Bài viết về Special features + hình if any | Duc |  |  | 4 | 5 | 4 | 5 | 100%
Export Corner | Huy |  |  | 4 | 5 | 4 | 5 | 100%
coding Index, Wall | Duc |  |  | 9 | 10 | 9 | 10 | 100%
Coding Home, Floor | Duong |  |  | 9 | 10 | 9 | 10 | 100%
CSS correction | Huy |  |  | 15 | 10 | 15 | 10 | 100%
Json updating | Trung |  |  | 6 | 3 | 6 | 3 | 100%
Checking and testing | Duc |  |  | 25 | 4 | 25 | 4 | 100%
Checking and testing | Duong |  |  | 25 | 4 | 25 | 4 | 100%
Checking and testing | Huy |  |  | 25 | 4 | 25 | 4 | 100%
Review | Team |  |  | 29 | 1 | 29 | 1 | 100%
Review | Huy with Teacher |  |  | 26 | 1 | 26 | 1 | 100%
Review | Huy with Teacher |  |  | 30 | 1 | 30 | 1 | 100%